## Pending tasks
Date entered | Priority | Description | Category | Comments | Status | Links 1 | Links 2
2022-09-08 | high | Scraper idle timer project |  | Need to talk to RCT
2022-09-08 | high | Excavator strategy adjustment to set off idle time |  | email sent to stakeholders for comments | in progress
2022-09-08 | high | 789C trucks replacement plan to be reviewed / condition report | Reliability | Prepared truck ranking system sheet / need to add frame condition score / Planner to plan the job in | In progress
2022-10-04 | high | PM Compliance check | Reliability | Emailed to planners /SOBR diggers are cleared
2022-06-03 | low | drill bit failure | Reliability | Matt is attending to site to check this failure / taken the broken bits / need to send the drilling lengths of each drill | In progress
| low | GET can be re-used after laser clading |  | explore the opportunity / 16-11-22 Apex will have a visit to see GET / visit done / need to send out samples to get quotes | In progress
2022-07-07 | Medium | Review 475 stratgey | Process | Meeting request sent / pre review done/ meeting to be held with komatsu to finalise strategy / meeting held/ need final feedback on fuel dosing system/sent final stratgey to planner / planner needs to update template | In progress
2021-09-20 | Medium | Engine Health dashboard | Reliability | reviewed CAT offer / need to go with CVA option 01 / sent email to asset team about the eng team decision / need to descuss the way forward / fuel consumption to be added/ sent info to Santhosh | In progress | Engine health dashboard
2021-09-20 | Medium | REX Lubrication action plan | Reliability | Lebelling of machines in progress / obsolete oil types were identified | In progress | Actions in progress
2021-09-20 | Medium | Specialist meeting actions | Reliability | Review actions in a separate sheet | In progress | Actions in progress
2021-09-20 | Medium | REX Reliability gap action plan | Reliability | Review actions in a separate sheet | Not started | Actions in progress
2021-11-30 | Medium | Tank level monitoring system | Lubrication | trial started at Mayara / trial in Maccoy started/ Pheonix Contact option is preferred / awaiting sensor quote / options emailed to team/PO sent/ installed / need calibration | In progress
2021-11-11 | Medium | Epiroc bush modification | Reliability | Need to process after the parts are ordered / sent to Shane for modification / awaiting details from vendor | In progress
2022-05-24 | Medium | add line to service sheet get fuel volume
2022-05-31 | Medium | check Hitachi sensor outputs and verify with FMS readings | Process | machine is in Tuesday / Hitachi rep will download on 20th June / contacted Bosco/ expecting Hexagon support / 1021 report to be downloaded by Tynan | In progress
2022-06-01 | Medium | Add Brake OPL to WOs | Process |  | In progress
| Medium | TPMS for 789 trucks | Safety
2022-11-14 | Medium | LV wash ramp solution analysis | GWD | quote requested from weldeast / need to request water canons from bendtech /water cannon designs and location / awaiting quote from Bendtech for option 2 / awaiting photos / Sent Capex request to Loreandro / need to decide the location / Check under wash robot solutions / automated wash solution found/ trial to be conducted / Enviro & structural assessments being done | In progress
2022-11-14 | Medium | New 1313 grader set up | Reliability | Emailed service kits to Westrac / Service kits sorted out / RCM being done / pending RCM meeting with specialist | In progress
2022-10-04 | Medium | Check suitability of balancer device for workshop | GWD | Emailed to stakeholders / informed Darren | In progress
2022-11-01 | Medium | add brake wear management to DI |  | DI added to system / need to calculate the costs /Draft in the system / Emma to confirm / clarifications sent out | In progress
2022-11-02 | Medium | Brake Dashboard meeting set up |  | eAM migration started on 08/09/2022 by IT team / Jared was going to get API | In progress
2022-11-03 | Medium | 980 wheel loader set up |  | LCC received / Engine OH interval needs clarification from CAT
2022-12-20 | Medium | Offline sampling station trial | ELW | quotes received
2022-12-20 | Medium | Hitachi oil (None-zinc oil) into Bulktank ( or 510 oil?) | Process
2022-11-04 | Medium | Send ball studs to test and verify

## Rex Lube
Action No. | Action Description |  | Loc'n |  | Mobile-H |  | Fixed-H |  | Mobile-W |  | Fixed-W |  | Comments
|  | Fundamental | Plan | Act | Plan2 | Act3 | Plan4 | Act5 | Plan6 | Act7 | Plan8 | Act9 | Act12
LUB-009 | Review Lube Management REX Target State Principles and Details with Reliability Eng's (L1 & 2) | FALSE | 2021-11-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a | L1 L2 Training added to SPA profiles in LMS
LUB-013 | Implement Actions to address GAPS in Loc'n Lube Structures, Roles & Resp to meet Target State | FALSE | 2021-10-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a | Developing business case for additional resource
LUB-016 | Implement L3 Tech. Training Plan for all Key Roles identified as critical for Location Lube Management | FALSE | 2021-09-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a | LMS to attach L3 training to engineers profiles/Requested Tamlyn to add to LMS
LUB-021 | Develop a Location Lubrication Register in line with REX Standard Template | FALSE |  | n/a | 2021-09-01 | c | 2021-08-01 | c | 2021-10-01 | i/p | 2021-10-01 | c | Need to be included in CDS
AUACDS-2051-3906, AUACDS-2051-3922
LUB-022 | Update the Location Lube Register with the target state lube reqmt's for each lubricated Equip. Item | FALSE |  | n/a | 2021-10-01 | c | 2021-08-01 | c | 2021-10-01 | i/p | 2021-10-01 | i/p | HUN registries done
LUB-024 | Carry out field GAP analysis of current lube set-up/configuration against target state standards | FALSE |  | n/a |  | n/a | 2021-12-01 | i/p |  | n/a | 2021-12-01 | i/p | Labelling of assets with correct lube types and accessories -
LUB-025 | Develop action plan to address GAPS in lube req'mts/config/set-up to target state standards | FALSE |  | n/a |  | n/a | 2021-12-01 | i/p |  | n/a | 2021-12-01 | i/p | Talk to Chris Martindale for Repair standard and include above
LUB-028 | Carry out GAP analysis of Lube Dispensing Processes, Tools & Equip. vs Target State req'mts | FALSE |  | n/a | 2021-09-01 | c | 2021-09-01 | c | 2021-10-01 | i/p | 2021-10-01 | i/p | AUACDS-2064-974
LUB-029 | Develop & implement actions to address GAPS in Lube Dispensing Processes, Tools & Equip. vs Target State | FALSE | 2021-12-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a | need to address the gaps identified by audits
LUB-033 | Develop & implement actions to address GAPS in Lube Labelling Processes, Tools & Equip. vs Target State | FALSE |  | n/a | 2021-10-01 | n/a | 2021-01-01 | c | 2021-10-01 | i/p | 2021-01-01 | c | Sent Hitachi oil specs to RN to obtain AML no
LUB-035 | Develop & implement actions to address GAPS in Lube Contamination Control Processes, Tools & Equip. vs Target State | FALSE | 2021-12-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a | check sheet 2064-977
LUB-039 | Develop & implement actions to address GAPS in Lube Sampling Processes, Tools & Equip. vs Target State req'mts | FALSE |  | n/a | 2021-11-01 | i/p | 2021-01-01 | c | 2021-01-01 | c | 2021-01-01 | c | Addressing issues related to updating dashboard /Linked to LUB-013
LUB-040 | Carry out GAP analysis of Lube Spills & Clean-up Processes, Tools & Equip. vs Target State req'mts | FALSE |  | n/a | 2021-10-01 | c | 2021-10-01 | c |  | n/a |  | n/a | check sheet 2064-977
LUB-041 | Develop & implement actions to address GAPS in Lube Spills & Clean-up Processes, Tools & Equip. vs Target State req'mts | FALSE | 2021-12-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a | Implementation
LUB-042 | Carry out GAP analysis of Lube Waste Management Processes, Tools & Equip. vs Target State req'mts | FALSE | 2021-12-01 | i/p |  | n/a | 2021-10-01 | c |  | n/a |  | n/a | check sheet 2064-978
LUB-043 | Develop & implement actions to address GAPS in Lube Waste Management Processes, Tools & Equip. vs Target State req'mts | FALSE | 2021-12-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a | Implementation
LUB-044 | Carry out GAP analysis of Lube Safe Mngmt & Handling Processes, Tools & Equip. vs Target State req'mts | FALSE | 2021-12-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a | check sheet 2064-973
LUB-045 | Develop & implement actions to address GAPS in Lube Safe Mngmt & Handling Processes, Tools & Equip. vs Target State req'mts | FALSE | 2021-12-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a | Implementation
LUB-047 | Develop Lubrication Routes that include ALL equipment on the Location Lube Register | FALSE |  | n/a |  | n/a | 2021-12-01 | i/p |  | n/a | 2021-12-01 | i/p | check sheet 2064-970
LUB-048 | Review and agree Field Verification Checksheet for Lube Route development ( routes to be Safe & Efficient) | FALSE |  | n/a |  | n/a | 2021-08-01 | c |  | n/a | 2021-08-01 | c
LUB-049 | Field Verify/Check all Routes with personnel who will be carrying out tasks on the routes ( refer checksheet) | FALSE |  | n/a |  | n/a | 2021-07-01 | c |  | n/a | 2021-07-01 | c
LUB-052 | Upload Lubrication Routes into CDS and eAM in line with REX Target State Standards Templates and Processes | FALSE |  | n/a |  | n/a | 2021-12-01 | i/p |  | n/a | 2021-12-01 | i/p | re-check CDS for validity of existing routes
LUB-057 | Review and agree standardised Lube System Health & Perf. Metrics, Review Processes, roles & resp | FALSE | 2021-12-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a | W:\ABS-Wa\WA Reliability Excellence Project\Implementation\WAO Lubrication Implementation\Metrics\OC Survey Results
LUB-058 | Implement Routine Group Leader Routine Work Auditing Process for Lube Routes | FALSE |  | n/a |  | n/a | 2021-12-01 | i/p |  | n/a | 2021-12-01 | i/p | AUACDS-2064-969 once a month
LUB-059 | Develop, agree & implement ongoing Training System, Roles & Resp to sustain Lube target State ( LMS/CDS/Alcoa Learn) | FALSE | 2021-11-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a | Duplication of LUB-003/4

## REX Reliability
STATUS
Action Description | SPA |  | Loc'n |  | Mobile-H |  | Fixed-H |  | Mobile-W |  | Fixed-W |  | WDL |  | Comments | Additonal comments
|  | Fundamental | Plan | Act | Plan2 | Act3 | Plan4 | Act5 | Plan6 | Act7 | Plan8 | Act9 | Plan10 | Act11 | Act12
Review and Sign-off REX Target State for Reliability with Location REX Reliability Mngmt Team | LOC RE SPA | TRUE | 2021-10-01 | n/s |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a | What does this actually mean?
Review and sign-off REX Target State for Reliability with REX Gov Team - Overview/Principles | LOC RE SPA | TRUE | 2021-10-01 | n/s |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a
Identify and agree Standardised Failure Reporting & Investigation Triggers | LOC RE SPA | TRUE | 2021-09-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a | Share triggers with team
Identify and agree Standardised Failure Investigation, Feedback, Follow-up/Reporting & Actions Mngmt Process | LOC RE SPA | TRUE | 2021-09-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a
Implement Standardised Loss Reporting Process | LOC RE SPA | TRUE | 2021-11-01 | n/s |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a
Implement Standardised Failure Investigation, Feedback, Follow-up/Reporting & Actions Mngmt Process | LOC RE SPA | TRUE |  | n/a | 2021-10-01 | i/p | 2021-09-01 | c | 2021-10-01 | i/p | 2021-09-01 | c |  | n/a
Identify Top 10 Bad Actors for Location ( key total cost drivers - mobile fleet, fixed plant ) | LOC RE SPA | TRUE | 2021-07-01 | c |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a
Develop fuel monitoring dashboard to report on trends and display on DDVM | S.K. | FALSE | 2021-12-01 | n/s |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a | Working with Nelis get data in to PI | Emailed Nelis
Develop Process to manage rolling Action Plans to Address Top 10 Bad Actors for Location ( eg EMS update, CAPEX etc) | LOC RE SPA | TRUE | 2021-10-01 | n/s |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a
Implement Action Plans to address TOP 10 Bad Actors for Location ( eg EMS update, CAPEX etc) | LOC RE SPA | TRUE | 2021-10-01 | n/s |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a
Train Reliability Engineers in the Development of a Quality Equip. Management Strategy (EMS)/STD Template | LOC RE SPA | TRUE | 2021-09-01 | c |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a | need a workshop with AH to train on digitiser
Train Reliability Engineers in the How to Translate EMS into Work Management Processes/CSMS | LOC RE SPA | TRUE | 2021-09-01 | c |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a | Reach out to Leith Place/Andrew H to organise training session on strategy digitiser
Review workflow for oil sample and result communication for mobile equipment | S.K. | FALSE | 2021-09-01 | n/s |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a | Discuss with Kevin (ALS) and contact Robin Nash (page 131 of WAO Lube strategy) | Invited David south and Robin to discuss this
Establish loss accoutning process to record planning and unplanned losses on a location as they occur | LOC RE SPA | TRUE | 2021-10-01 | i/p |  | n/a |  | n/a |  | n/a |  | n/a |  | n/a
Develop standardised metrics for mobile equipment availabilty | LOC RE SPA | TRUE |  | n/a | 2021-08-01 | c |  | n/a | 2021-08-01 | c |  | n/a |  | n/a
Develop Reliabilty Metrics Dashboard | J.D. | TRUE |  | n/a | 2021-10-01 | i/p |  | n/a | 2021-10-01 | i/p |  | n/a |  | n/a
Impliment standard perfomrance metrics in DDVM dashboard | LOC RE SPA | TRUE |  | n/a | 2021-11-01 | n/s |  | n/a | 2021-12-01 | n/s |  | n/a |  | n/a

## specialist meetings
Fleet | Action | Comments | Links | Status
Service trucks | service sheet change | Emailed to Phil M |  | In progress
Service trucks | Wash ramp for service trucks | John S to inspect structure |  | In progress
Service trucks | Arrange scania training | Emailed contacts to Brad |  | In progress
Trucks | Fuel tank refurb | Tank is at Line x | quote - Bendtech | In progress
Dozers | Change of thermostats of 1417 | Pb Trend analysis - Pb at 0 ppm on 01-nov-2021 | ALS trend | In progress
Trucks | add filter cutting in to worksheet | emailed to Phil M and DL | filter rating chart | In progress
Loaders | fill AML 532 Tank | Speak to Shannon |  | Done
Low Loaders | Trailer deflection | Requested drawings from OEM / cannot find the deisgn limits as many modifications done | measurements | On hold
Service trucks | Contact asset team for replacement strategy | 4177 is getting replaced |  | complete
Service trucks | Denso tape harnesses before delivery | speak to Jeremy |  | Done

## Completed tasks
Date entered | Priority | Description | Category | Comments | Status | Links 1 | Links 2
2021-09-20 | High | RCA report of Strut failure | Safety | Failure report received / reviewed recommendations | Complete | FA report
2021-09-20 | High | ALS transistion | Reliability | transitioned fully | Complete |  | CAT report
2021-11-22 | High | 1293 low loader oil cooler alarm | Reliability | Adjustment done by Ash | Complete
2021-09-23 | High | RCM for Hitachi truck | Reliability | Eamailed strategy to Cath to upload to digitizer | Complete | RCM sheet
2021-09-20 | Low | Increase productivity by running trucks at higher TKPH values which is enabled by live truck tyre pressure and temperature monitoring system | Productivity | need to revise the business case /evaluate current system and fine tune | On hold
2021-10-01 | Low | Pressure test the fittings Hytorque | Safety | Quote forwarded to Sarah | On hold
2021-09-21 | Medium | RAD gun RCA | Safety | Forwarded preliminary RCA to Jorge / Have to learn more Thursday | Complete | RCA Chart
2021-09-20 | Medium | MOH commissioning sheet | Reliability | Update the list | Complete | Check list | Comparisons - Bendtech
2021-10-27 | Medium | Business case - Air filter project | Cost saving | Business case prepared / to be reviewed by JD / DI opened by JD | Complete
2021-09-30 | Medium | 1309 grader fire supression system blocking operator view | Safety | MWR booked in / emailed Donny to arrange job | Done
2021-09-20 | Medium | Paint fuel and hydraulic tanks | Reliability | Line X done / Fuel Tank at stores / need monitoring | Done | Comparisons
2021-09-23 | Medium | EMS training | Reliability | Training done | Complete
2021-10-20 | Medium | Bad trans oil sample action - Dozer 1419 | Reliability | Tranny was flushed on 18-10-2021 / sample taken again 08-11-2021/trending down | Complete | Trend
2021-10-21 | Medium | Loader and excavator strategy review | Reliability | Emailed to JD to review / Loader strategy done / need to include that in EAM | emailed
2021-12-01 | Medium | RCA tilt cylinder | Reliability | Mod approval to be sent to Calcott / approval sent / new cylinder to be purchased from Westrac | Complete
2021-09-20 | Medium | EPIROC hammer re-build | Cost saving | Process in place | Complete | Quotation
2021-09-29 | Medium | 1297 Babylon engine oil sample check | Cost saving | Fe is at 4 ppm on 23-sep-2021 / Low oil pressure alarm triggered | Did not progress | ALS trend
2021-12-20 | Medium | Sensor polling frequency | Reliability | email from Mitch / discuss with Trev/ new frequencies sent to Mitch | Complete |  | Folder
2021-12-16 | Medium | Hitachi truck tyre strategy | Reliability | Cath to upload to EMS | Complete
2021-09-20 | Medium | Get the latches fitted to the doors of the graders | Reliability | 1308/1309 are completed | completed | WO for latches
2021-09-20 | Medium | Review service truck maintenance strategy and come up with improvement opportunities to increase reliability of the service trucks | Reliability | meeting scheduled | complete | Presentation
2022-01-19 | Medium | Workshop computer setup for iqan3 | Process | done | completed
2022-01-21 | Medium | Scraper 1526 front tranny RCA | Reliability | Found normal wear | completed
2022-02-16 | High | Nano filter slides with business case | Cost saving | trialed | completed
2021-09-24 | Medium | Pin installer | Safety | Luke and Siobhan to update risk register | Did not progress
2022-01-27 | High | 2007 truck brake failure RCA | Reliability | Analysis sent with action plan : SWI / SWI sent | completed
2022-01-17 | Medium | Hitachi grease MIMS | Process | Approved and active now | complete
2022-02-16 | High | quality plan for low loaders brakes | Safety | active | complete
2022-03-15 | High | Open Di for Nano filter project | Cost saving | DI opened | completed
2021-12-24 | Medium | 789C air filter conversion to 789 D filter | Cost saving | trial started / trial proved no significant improvement in filter life | Completed
2022-02-08 | Medium | Loader-1065 failure rate is rising | Reliability | emailed info to Dave / engine OH done / harnesses replaced / need monitoring as part of meeting actions | Completed
2022-05-11 | Medium | cut filter line change | Reliability | current arrangement is ok | Completed
2021-11-30 | High | ALS work review | Reliability | Go live from Monday / review WR from ALS / new PO to be raised / done | Complete
2021-09-20 | High | Introduce a procedure to record truck brake wear measurements and establish baselines for truck brakes which can increase the safety of haul - trucks while achieving more accurate brake wear prediction | Safety | Implement action plan / Rajesh to romove quality plan / OPL to be aproved / emailed superviosrs about the worksheet /emailed Dean to verify brake wear of all trucks with new sheet / ammend the QP to match the activities / set up activity to re-calibrate Birrana gauges / meeting scheduled on thursday / latest OPL released with instructions | complete | Brake wear calculations
2022-05-23 | Medium | Download PSR from trucks and check fuel volume |  | checked once / awaiting second report /sent details to Santhosh /calculated average consumption | complete
2021-09-20 | Low | REX Precision gap action plan | Process | APEX comes 2 times per year to calibrate all tools based on the sticker | Did not progress
2021-09-20 | Low | Caltex to Mobil transition | Process | Need to review tranch 4 | Complete | Updated list
2022-05-29 | low | check tyre wear of Hitachi | Process | got the readings into excel sheet | Complete
2022-02-10 | Medium | 789C strategy review | Reliability | sent Jorge for review | complete
2022-05-27 | Medium | Fuel quality check - Huntly bulk | Process | sent email to Chris | complete
2022-05-25 | Medium | Hitachi hyd oil change interval review | Cost saving | Emailred to the team / quantify the savings / need to wait till 09/2023 | complete
2022-06-04 | high | Check air start issues of trucks | Reliability | Start with the most problematic trucks/ create WRs | complete
2022-07-12 | Medium | scraper dirt in samples level check and update | Reliability | Email sent with the analysis | complete
2022-07-12 | Medium | 1530 rear engine sillicon level high. Raise WR | Reliability | Raised WR to check dirt entry | Complete
2022-07-10 | Medium | scraper brake change interval review . Check the variance and review | Cost saving | review done | complete
2022-07-16 | Medium | Remove non-relevant assets from rex dashboard | Reliability | done | complete
2022-07-07 | Medium | scraper service intervals (too short) | Process | cost analysis emailed to team/ need to get approval to change from time-based to hours / need to talk to JD / changed to hr based strategy | complete
2021-12-24 | Medium | Steering cylinder failure - Scraper | Safety | Andrew to share dimensions / track cylinder by stamped number / start tracking cylinders with excel sheet / setting up eAm activity for NDT / awaiting date to start NDT on one scraper / NDT done and process will continue | complete
2021-09-20 | Medium | Epiroc drill parts order | Reliability | Emailed to Jason D to order parts / awaiting Anthony approval /awaiting PO / awaiting parts / first changeout done | complete
2022-02-15 | Medium | Low loader repair history deep dive to understand structural repairs | Reliability | Inspection will be done on 03/05/22 , need to check Wos for any repairs done in past and no of hours spent on 3205 / a thrid party report was given about the condition | complete
2022-05-21 | Medium | target payload study | Reliability | emailed coco. Need to calibrate 1288. emailed Mitch about the limitations and suggestions /awaiting results of next load study /1288 calibrated | complete
2022-07-07 | Medium | Activity for scarper crack inspection | Reliability | Added to meeting minutes / emailed to Hayden the change / added the operation to activity | complete
| Medium | Brake data analysis 1297 | Safety | POS 3 trending down / emailed to AP / recommended birrana adjustment /brake pack chanaged | complete
2022-11-01 | Medium | Craete CPQRT for idle timer | DI | Sent to Yvonne | complete
2022-07-15 | Medium | Verification of strut pressure checks | Process | 1288 was calibrated/ 2012 /1285/9633/1287/1299/1279/1289/1298/2011/1295/2006/1285/1286/1287 were recently calibrated | complete
2022-11-14 | Medium | Rim changeout details of hired trucks |  | requested info from SMS/ received part of the NDT reports / received all reports | In progress
2022-09-07 | Medium | Drill strategy review | Reliability | Breakout cylinder / grease pump were put on condition based | complete
2022-07-15 | Medium | scraper crack inspection schedule / line up with hose inspection | Reliability | emailed changes to hayden / added to standard activity in eAM | Complete
2021-09-20 | Medium | Create KPI matrix for Reliability of equipment | Reliability | Cost per hour to be added to the matrix / WO text detection / add Cummalative MTBF | Complete | Link to Jupyter app | Link to web app
2021-09-20 | Medium | to dynamically test the truck fan drive deflection which can provide more accurate readings and reduce truck downtime and unnecessary fan drive repair costs | Reliability | Monitoring the readings /awaiting tool cable /due on 17 June / process re-started / used as additional input for fan drive changeout decision making process | Complete
2022-05-22 | Medium | Ball stud instructions | Process | awaiting tool price / 6K tool / need to send out the instructions to Supervisors / email sent to supervisors/ a tool needs to fabricated using a new ball stud /AL Pash is working on this | In progress
2022-05-27 | Medium | Track pin hours of Loaders | Reliability | Nat to send the filled template / review template /emailed to Rajesh / hours are now on Mining tool | Complete
2022-05-20 | Medium | Line x tank | Reliability | awaiting quote / received quote /2nd tank to be sent / 1st tank is fitted to truck and running / 2nd Tank done | Complete

## Trends
1419 Transmission